## Example (filled)
Run of Show
Talvenor annual dinner · Riverside Hall, Chicago, IL · Thursday, November 12, 2026 · 120 guests · Version 3, issued November 9
Illustrative example. One line per moment: a clock time, one cue, one owner. Quantities and menus stay on the BEO.
Venue coordinator | Mia Turner (owns this document)
Client lead | Sarah Chen, Talvenor (decides on the day)
Spaces | Main Hall, Terrace, loading dock
Time | Duration | Cue | Space | Owner | AV / tech | Notes
Load-in and setup
2:00 PM | 60 min | Venue access. Tables and chairs, 12 rounds of 10 | Main Hall | Floor captain |  | Table plan v3 from the client
2:30 PM | 90 min | AV build: PA, 3 mics, projector, screen | Main Hall | AV technician
3:00 PM | 60 min | Florist: 12 centerpieces, terrace planters | Main Hall, Terrace | Florist |  | Loading dock slot 3:00 to 3:30 PM
4:30 PM | 15 min | Sound check, client slides on screen | Main Hall | AV technician | Slides on USB
5:00 PM | 30 min | DJ load-in and line check | Main Hall | DJ | DJ on house PA
Doors and guest arrival
5:30 PM | 15 min | Staff briefing: timeline, table plan, allergies | Kitchen pass | Venue coordinator |  | Each owner reads their own lines
6:15 PM | 10 min | Final walk-through with the client lead | All spaces | Venue coordinator | Lights preset
6:30 PM | 50 min | Doors open. Cocktail hour, passed hors d'oeuvres | Terrace | Floor captain, bar | Background music, low | Heaters on at 6:00 PM
7:20 PM | 10 min | Guests invited to the Main Hall | Terrace to Main Hall | Floor captain | Music fade
Program, speeches and cues
7:30 PM | 15 min | Guests seated | Main Hall | Floor captain | Lights to 40%
7:45 PM | 5 min | Welcome speech (Sarah Chen) | Stage | Client | Mic 1, lectern spot
8:00 PM | 30 min | First course served | Main Hall | Kitchen, floor |  | Table 4: no pecans (nut allergy)
8:40 PM | 40 min | Main course served | Main Hall | Kitchen, floor |  | 12 vegetarian: tables 3, 7, 11
9:30 PM | 15 min | Dessert and coffee | Main Hall | Kitchen, floor |  | Gluten-free: tables 2, 9
9:40 PM | 5 min | Sparkling wine poured for the toast | Main Hall | Bar |  | Sparkling cider for alcohol-free guests
9:45 PM | 10 min | Award presentation and toast | Stage | Client | Slides 12 to 18, mic 2 | Presenter: Talvenor CEO
9:55 PM | 5 min | Room flip: 2 tables cleared for the dance floor | Main Hall | Floor captain | House lights 60%
Entertainment
10:00 PM | 120 min | DJ set | Main Hall | DJ | Dance lighting on | Sound limit from 11:00 PM
Close
11:15 PM |  | Last call announced | Main Hall | DJ, bar | Mic 2
11:30 PM |  | Bar closes | Bar | Bartenders
12:00 AM | 15 min | Music off, house lights up, guests leave | Main Hall | Venue coordinator | Lights 100% | Rideshare pickup at the main door
Teardown and load-out
12:15 AM | 15 min | Damage walk-through with the client lead | All spaces | Venue coordinator |  | Noted and signed on the BEO
12:30 AM | 45 min | DJ and AV load-out | Main Hall | DJ, AV technician |  | Loading dock opens 12:30 AM
1:30 AM |  | Venue reset, doors locked | All spaces | Floor captain |  | Lost and found logged
Free template by Joinways (joinways.app). In Joinways, the event timeline sits next to the quote and the BEO.

## Blank run of show
Run of Show
[Event] · [Venue] · [Date] · [Headcount] · Version ____, issued ____
Clock times, not durations alone. A line without an owner is a line nobody executes.
Venue coordinator
Client lead
Spaces
Time | Duration | Cue | Space | Owner | AV / tech | Notes
Load-in and setup
Doors and guest arrival
Program, speeches and cues
Entertainment
Close
Teardown and load-out
Free template by Joinways (joinways.app). In Joinways, the event timeline sits next to the quote and the BEO.